## Tracker
HABULAN RUSH — 12-Day Production Tracker
Source: GDD v2.0 §21 (Oct 7–18 build window). Edit blue cells only: Start Date, Owner, Status, Notes. Dates recalculate from Start Date.
Start Date (Day 1) |  | 2026-10-07 |  | Overall % Done | 0% |  | Blocked | 0
Legend: yellow/blue = input · P0 = must ship (MVP) · P1 = should ship · P2 = stretch. Owner roles are placeholders — replace with team names.
ID | Day | Date | Phase | Task | Area | Owner | Priority | Status | Notes
T01 | 1 | 2026-10-07 | Design Lock | Approve GDD v2.0 and resolve open items from GDD System Review | Design | Lead | P0 | Not Started
T02 | 1 | 2026-10-07 | Design Lock | Create repository, folder structure, branching rules, AI_LOG.md | Tech | Programmer | P0 | Not Started
T03 | 1 | 2026-10-07 | Design Lock | Create Config module skeleton (all balance numbers from GDD) | Tech | Programmer | P0 | Not Started
T04 | 2 | 2026-10-08 | Design Lock | Finalize Config values with Balance Workbook baseline | Design | Designer | P0 | Not Started
T05 | 2 | 2026-10-08 | Design Lock | Assign module ownership (Match, Tag, Skill, UI, Movement) | Management | Lead | P0 | Not Started
T06 | 2 | 2026-10-08 | Design Lock | Set up asset source list / disclosure log | Management | Lead | P0 | Not Started
T07 | 3 | 2026-10-09 | Core Loop | MatchService: state machine MS_01–MS_06 + shuffle bag | Code | Programmer | P0 | Not Started
T08 | 3 | 2026-10-09 | Core Loop | Barangay Kalsada greybox (150x150, 8 spawns, vaults, low gaps) | Level | Artist | P0 | Not Started
T09 | 4 | 2026-10-10 | Core Loop | MovementController: walk, sprint, stamina, dash, slide | Code | Programmer | P0 | Not Started
T10 | 4 | 2026-10-10 | Core Loop | Taya timer + round timer replication | Code | Programmer | P0 | Not Started
T11 | 5 | 2026-10-11 | Core Loop | TagService: server-validated touch tag + tag transfer | Code | Programmer | P0 | Not Started
T12 | 5 | 2026-10-11 | Core Loop | Safe Window, speed boost and Lock Delay on tag | Code | Programmer | P0 | Not Started
T13 | 6 | 2026-10-12 | Core Loop | Pounce (wind-up, lunge, miss stun, cooldown) | Code | Programmer | P0 | Not Started
T14 | 6 | 2026-10-12 | Core Loop | HUD v1: role banner, timer, scoreboard, stamina | UI | UI Dev | P0 | Not Started
T15 | 6 | 2026-10-12 | Core Loop | Core loop internal playtest (4+ players) | QA | QA | P0 | Not Started
T16 | 7 | 2026-10-13 | Skills + Diskarte | TargetLockController: soft lock, lock break, lock cooldown | Code | Programmer | P0 | Not Started
T17 | 7 | 2026-10-13 | Skills + Diskarte | Skill Draft UI + PickSkill remote (12 s) | UI | UI Dev | P0 | Not Started
T18 | 8 | 2026-10-14 | Skills + Diskarte | SkillService: Runner skills RS_01–RS_03 | Code | Programmer | P0 | Not Started
T19 | 8 | 2026-10-14 | Skills + Diskarte | SkillService: Taya skills TS_01–TS_03 | Code | Programmer | P0 | Not Started
T20 | 8 | 2026-10-14 | Skills + Diskarte | Skill VFX/SFX tells v1 (placeholder acceptable) | Art/Audio | Artist | P1 | Not Started
T21 | 9 | 2026-10-15 | Skills + Diskarte | Diskarte meter: gain events, anti-snowball rules, reset per round | Code | Programmer | P0 | Not Started
T22 | 9 | 2026-10-15 | Skills + Diskarte | Diskarte Moves: LIKSI, BANTAY, PUSO | Code | Programmer | P0 | Not Started
T23 | 9 | 2026-10-15 | Skills + Diskarte | Skill counter tests (1v1) and first balance pass | QA | QA | P0 | Not Started
T24 | 10 | 2026-10-16 | Rush Systems | Barangay Rush: Court Rush event (telegraph 2–3 s, counter-route) | Code | Programmer | P0 | Not Started
T25 | 10 | 2026-10-16 | Rush Systems | Phase controller: SIMULA / BARANGAY RUSH / HULING HABOL timings | Code | Programmer | P0 | Not Started
T26 | 11 | 2026-10-17 | Rush Systems | Huling Habol presentation: banners, music layers, countdown | UI/Audio | UI Dev | P0 | Not Started
T27 | 11 | 2026-10-17 | Rush Systems | Clutch callouts + round-end recap + Match MVP screen | UI | UI Dev | P1 | Not Started
T28 | 11 | 2026-10-17 | Rush Systems | Rush/Habol readability test with a spectator | QA | QA | P0 | Not Started
T29 | 12 | 2026-10-18 | Second Map | Binaha na Baryo greybox + flood level logic (only if core stable) | Level | Artist | P1 | Not Started
T30 | 12 | 2026-10-18 | Second Map | Tutorial blockout: steps 1–4 (move, sprint, dash, tag) | Code/UI | UI Dev | P0 | Not Started
T31 | 12 | 2026-10-18 | Second Map | Private lobby code + spectator camera (follow Taya) | Code | Programmer | P0 | Not Started
T32 | 12 | 2026-10-18 | Second Map | Day-12 checkpoint: go/no-go on second map and stretch cuts | Management | Lead | P0 | Not Started
Formulas:
Date = C3+[Day]-1

## Daily Summary
Daily Summary — Day 1 to Day 12
Counts are formulas from the Tracker. Fill the blue columns at end of each day.
Day | Date | Phase | Tasks | Done | In Progress | Blocked | % Done | Hours Planned | Hours Actual | Blockers / End-of-day note
1 | 2026-10-07 | Design Lock | 3 | 0 | 0 | 0 | 0%
2 | 2026-10-08 | Design Lock | 3 | 0 | 0 | 0 | 0%
3 | 2026-10-09 | Core Loop | 2 | 0 | 0 | 0 | 0%
4 | 2026-10-10 | Core Loop | 2 | 0 | 0 | 0 | 0%
5 | 2026-10-11 | Core Loop | 2 | 0 | 0 | 0 | 0%
6 | 2026-10-12 | Core Loop | 3 | 0 | 0 | 0 | 0%
7 | 2026-10-13 | Skills + Diskarte | 2 | 0 | 0 | 0 | 0%
8 | 2026-10-14 | Skills + Diskarte | 3 | 0 | 0 | 0 | 0%
9 | 2026-10-15 | Skills + Diskarte | 3 | 0 | 0 | 0 | 0%
10 | 2026-10-16 | Rush Systems | 2 | 0 | 0 | 0 | 0%
11 | 2026-10-17 | Rush Systems | 3 | 0 | 0 | 0 | 0%
12 | 2026-10-18 | Second Map / Checkpoint | 4 | 0 | 0 | 0 | 0%
Total |  |  | 32 | 0 | 0 | 0 | 0% | 0 | 0
Formulas:
Date = Tracker!$C3+[Day]-1

## Rules
Tracker Rules & Scope Guard
• This tracker covers the 12-day build window (Oct 7–18). Oct 19–25 (polish, freeze, testing, submission) is in the Production & Launch Plan.
• SCOPE LOCK (GDD §20): never cut the tutorial or core tag loop to build a stretch feature. Cut P1/P2 first.
• Day-12 checkpoint decides whether Binaha na Baryo continues and which P1 items are cut.
• A task is Done only when it works in a live multiplayer server test, not just in Studio solo.
• Log any AI-assisted work in AI_LOG.md the same day it is used.