HABULAN RUSH

Production & Launch Plan

Version 1.0 • Competition: Level Up 3.0 Esports Game Dev Challenge • Deadline Oct 25, 2026

# 1. Objective

Ship a polished, stable Classic Habulan build with Barangay Kalsada and (if stable) Binaha na Baryo, a working tutorial, private lobbies and spectator camera by Oct 25, 2026. "Launch" means the competition submission and demo; there is no monetization.

# 2. Schedule

| Dates | Phase | Deliverables | Gate |
| --- | --- | --- | --- |
| Oct 7–8 | Design lock | GDD v2.0 approved, Config final, roles assigned, repo | Confirm GDD System Review defaults |
| Oct 9–12 | Core loop | Match, tag, movement, Taya Timer, scoreboard, Kalsada greybox | Alpha: 3 clean matches |
| Oct 13–15 | Skills + Diskarte | Draft, 3+3 skills, Diskarte and Moves | All skills pass 1v1 |
| Oct 16–17 | Rush systems | Court Rush, Huling Habol, clutch feedback | Beta: all P0 features in |
| Oct 18–19 | Second map | Binaha na Baryo only if stable; tutorial and lobby/spectator finish | Go/no-go on map (Oct 18) |
| Oct 20–21 | Polish + freeze | Art, UI, sound, performance, tutorial; feature freeze | Freeze Oct 21 evening |
| Oct 22–23 | Testing | Six-player playtests, tuning, bug fixes | Release candidate |
| Oct 24 | Submission package | Trailer, demo, synopsis, forms, disclosure check | Package review |
| Oct 25 | Deadline | Submit final package early in the day | Submitted |

# 3. Team and responsibilities

| Role | Responsibilities | Count |
| --- | --- | --- |
| Producer / Lead | Schedule, scope decisions, submission, disclosure log | 1 |
| Game Designer | Config, balance, event design, playtest analysis | 1 |
| Programmers | Services, controllers, networking (see TDD) | 2 |
| UI Developer | HUD, screens, tutorial | 1 |
| Artist / Builder | Maps, VFX, characters | 1–2 |
| Audio | Music, SFX, voice | 1 |
| QA | Test cases, bug tracking, playtest sessions | Shared by all |

Adjust to the real team size; one person may hold several roles. Replace role names with names in the Production Tracker.

# 4. Scope management

| Priority | Items | Rule |
| --- | --- | --- |
| P0 (must) | Classic FFA, 3 rounds, tag + timer, movement, 3+3 skills, Diskarte, Barangay Rush, Huling Habol, Kalsada, tutorial, private lobby, spectator camera | Never cut |
| P1 (should) | Binaha na Baryo, clutch popups and recap, voice lines, mobile layout options | Cut at Day-12 checkpoint or freeze if behind |
| P2 (stretch) | Recycling Hub, Palengke, Palayan, Time Trial, Team Habulan, Last Runner Standing, audience voting | Only after freeze if stable; otherwise out |

- Feature freeze Oct 21 evening: after it, only bug fixes, tuning and polish with team approval.

- Daily 10-minute stand-up; update the Production Tracker at end of day.

# 5. Risk register

| Risk | Impact | Prob. | Mitigation | Owner |
| --- | --- | --- | --- | --- |
| Feature creep | High | Med | Scope lock; stretch only after freeze | Producer |
| Tutorial skipped | High | Med | Built by Oct 12 (blockout) and finished before polish | UI Dev |
| Lag disputes | High | Med | Server authority, rewind, logs | Programmer |
| Diskarte snowball | High | Low | Temporary effects; per-round reset; playtest | Designer |
| Asset/AI disclosure issue | High | Low | Source list and AI_LOG.md from day 1; audit Oct 24 | Producer |
| Team member unavailable | Med | Med | Two people know each module; daily integration | Producer |
| Studio/Roblox outage near deadline | High | Low | Submit by noon Oct 25 and keep a published backup version | Producer |
| Map event feels random | Med | Med | Telegraph; counter-route; spectator test | Designer |

# 6. Launch (submission) plan

## 6.1 Submission package

| Item | Owner | Due | Status |
| --- | --- | --- | --- |
| Published game, public or per rules, tested from a clean account | Programmer | Oct 23 | ☐ |
| Gameplay trailer (60–90 s): hook, tag, skills, Diskarte, Rush, Huling Habol, clutch | Artist/Audio | Oct 24 | ☐ |
| Demo plan: 6-player match script, spectator view, private lobby code | Producer | Oct 24 | ☐ |
| Game synopsis: pitch, theme relevance (Philippine games, DRRM, circular economy), esports features | Designer | Oct 24 | ☐ |
| AI / asset disclosure with AI_LOG.md and source list | Producer | Oct 24 | ☐ |
| Entry forms and team details per competition rules | Producer | Oct 24 | ☐ |
| Final submission | Producer | Oct 25 (aim: before noon) | ☐ |

## 6.2 Go / no-go checklist (Oct 24)

- Two consecutive clean 6-player matches on PC and one on mobile.

- No open Blocker or Major bugs; tutorial completes for new players.

- Pounce success within 40–60% in the last 3 sessions; match duration 8–10 min.

- Trailer, synopsis, disclosure and forms complete and reviewed by two people.

- Published version matches the tested build; backup version saved.

# 7. Communication and tracking

- Tracker: Habulan_Rush_Production_Tracker.xlsx (12-day build window); Balance: Habulan_Rush_Balance_Workbook.xlsx.

- Stand-up: 10 minutes daily; blockers recorded in the Daily Summary sheet.

- Decisions about scope are made by the Producer with the Designer; changes recorded in the GDD revision note.

# 8. Post-submission

- Collect judge and audience feedback for the demo; log it against GDD features.

- Plan stretch items (more maps, modes, audience voting) only after the competition result.