HABULAN RUSH

QA Test Plan

Version 1.0 • Derived from GDD v2.0 §17 and §19 • Test window Oct 9–23

# 1. Scope and objectives

Verify that Habulan Rush is fair, stable, readable and complete for competition submission. Priority order: core tag loop, tutorial, skills, Diskarte, Barangay Rush/Huling Habol, spectator and lobbies, then stretch features.

# 2. Test environments

| Environment | Details |
| --- | --- |
| Studio local server | Fast iteration; 1–2 clients |
| Live private server | 6-player sessions, real latency; main balance source |
| Devices | PC (mid-range), phone (Android and iOS), console client if available |
| Network | Normal and throttled (150 ms, 3% loss) at least once per build |

# 3. Entry and exit criteria

| Stage | Entry | Exit |
| --- | --- | --- |
| Alpha (Oct 12) | Core loop playable | No crash in 3 full matches |
| Beta (Oct 16) | Skills, Diskarte, Rush in | All P0 test cases run; blockers closed |
| Feature freeze (Oct 21) | Tutorial and core complete | No open P0/P1 bugs; stretch cut |
| Release candidate (Oct 23) | Freeze build | 2 consecutive clean 6-player matches on PC and mobile |

# 4. Test cases

| ID | Area | Test | Pass criteria | Pri |
| --- | --- | --- | --- | --- |
| T-CORE-01 | Match flow | Run lobby → 3 rounds → match end | All states occur in order; duration 8–10 min | P0 |
| T-CORE-02 | Scoring | Compare ranks and points to Balance Workbook Scoring sheet | Exact match, ties handled | P0 |
| T-CORE-03 | First Taya | 12 matches with 6 players | Each player first Taya before any repeat within a bag | P0 |
| T-MOV-01 | Movement | Sprint until empty, rest, recover | Values match Config; no sprint at 0 | P0 |
| T-MOV-02 | Dash/slide | Dash and slide cooldowns, low gap pass | Cooldowns exact; slide passes low gap | P0 |
| T-TAG-01 | Touch tag | Tag at 2.9 and 3.1 studs | Valid at 2.9, rejected at 3.1 | P0 |
| T-TAG-02 | Pounce | Hit, miss, spam | Miss stuns 1.0 s; cooldown 3 s; spam punished | P0 |
| T-TAG-03 | Transfer | Tag and observe windows | Safe 2 s, boost 2 s, Lock Delay 1 s; one TagEvent | P0 |
| T-TAG-04 | Lag | Tag test at 150 ms and 300 ms | No false tag beyond rewind cap; disputed rate < 5% | P0 |
| T-LOCK-01 | Target lock | Break via dash, cover, line of sight | Lock breaks; 4 s lock cooldown | P1 |
| T-SKL-01..06 | Skills | Each skill: use, counter, edge case in 1v1 | Effect matches spec; counter exists; no guarantee | P0 |
| T-DSK-01 | Diskarte | Earn from every action; check anti-snowball | Gains per Config; repeats blocked; reset per round | P0 |
| T-DSK-02 | Moves | Use LIKSI, BANTAY, PUSO | Effect and expiry correct; PUSO does not stack | P0 |
| T-RSH-01 | Barangay Rush | Observe event at 100 s | 2–3 s warning; counter-route exists; nobody removed | P0 |
| T-HAB-01 | Huling Habol | Check 50, 30, 15, 10, 5 s cues | All cues fire; no stat change; round ends at 0 | P0 |
| T-SPC-01 | Spectator | Observer watches 2 min without help | Names Taya and leader; understands events | P0 |
| T-TUT-01 | Tutorial | New players complete it | ≥ 90% complete in 60–90 s; understand win rule | P0 |
| T-NET-01 | Disconnect | Taya and Runner leave mid-round | Nearest Runner becomes Taya; leaver ranked last | P0 |
| T-LOB-01 | Private lobby | Join by code from 2 devices | Joins; map vote works | P0 |
| T-UI-01 | Mobile UI | Play full round on phone | All actions reachable; HUD readable | P0 |
| T-PERF-01 | Performance | 8-player match on mid-range phone | Average 30+ FPS; no memory growth over 3 matches | P1 |
| T-ACC-01 | Accessibility | Colorblind mode, text size | Role distinguishable without color | P1 |

# 5. Balance testing

- Use the Balance Workbook Playtest Log for every round: pounce attempts and hits, touch tags, dodges, Taya Time, duration, clarity answer.

- Targets: pounce success 40–60%, match 8–10 min, no skill with a pick rate above 60% across two sessions, Diskarte Moves 1–2 per role per round.

- Pass requires at least 6 sessions of 6 players, 2 per map.

# 6. Bug management

| Severity | Definition | Fix target |
| --- | --- | --- |
| Blocker | Crash, cannot finish match, score wrong | Same day |
| Major | Core system incorrect or unfair; mobile unusable | Within 24 h |
| Minor | Visual/audio flaw, text, small UX | Before freeze if time |
| Polish | Nice to have | After freeze only if safe |

Each bug record: ID, build, steps, expected, actual, severity, owner, status, screenshot or video.

# 7. Schedule

| Dates | Activity |
| --- | --- |
| Oct 9–12 | Core loop tests; first 1v1 and 4-player sessions |
| Oct 13–17 | Skill, Diskarte, Rush tests; first 6-player sessions |
| Oct 18–21 | Regression, tutorial and mobile test; freeze |
| Oct 22–23 | Six-player playtests, tuning, release candidate tests |
| Oct 24 | Submission build smoke test (demo and trailer capture) |